## Sheet1
May be for Q3
|  | 2D Overlay | Model views / Viewpoints | Federartion | Searchsets | Permissions | Misc | Dependencies | Mobile | Origin Controller | Appearence Profiler
Critical - right now in Q2 |  | Multilevel | Multilevel folder | Hide temp elements in Project View | Search Constructor | PDM permissions to federated Scene | New Header UI | Save Viewpoint with Search sets | Performance | Origin Controller UI | Create Appearence Profiles
High - definitely Q2 |  | Elevation Mapping | Bulk Actions | Multiple Federated scenes? | Search Management | Admin and non Admin permissions |  | Markups save in a view point | Offline Model? | Map box UI? | Save with Views
medium - 30% chance of Q3 |  | Bulk Actions | Share Views - by clicking share button | Permissions | Permissions |  |  | Create viewpoints with searchsets |  |  | Save with Search sets
low - may be Q3 / Q4? |  | Permissions | Save with Markups | Versioning | Public / Private Search |  |  | Import Revit sheets
|  | Premapped Revit sheets? | Permissions |  | Import Searchset - Auto / Manual? |  |  | Draggable Windows
|  |  | Public / Private Views |  | Quick Search / Global Search
Auto Import from Navisworks
In 2D Views Panel, when clicking to 'view' an overlay, we will apply a section but not change the camera until we hear feedback from users

## Sheet2
Functionality | Feature | Priority
**2D Overlay** | Multilevel | [Add Priority Here]
**2D Overlay** | Elevation Mapping | [Add Priority Here]
**2D Overlay** | Bulk Actions | [Add Priority Here]
**2D Overlay** | Permissions | [Add Priority Here]
**Model views / Viewpoints** | Multilevel folder | [Add Priority Here]
**Model views / Viewpoints** | Bulk Actions | [Add Priority Here]
**Model views / Viewpoints** | Share Views | [Add Priority Here]
**Model views / Viewpoints** | Save with Markups | [Add Priority Here]
**Model views / Viewpoints** | Permissions | [Add Priority Here]
**Model views / Viewpoints** | Public / Private Views | [Add Priority Here]
**Model views / Viewpoints** | Import from Navisworks | [Add Priority Here]
**Federartion** | Hide temp elements in Project View | [Add Priority Here]
**Federartion** | Multiple Federated scenes? | [Add Priority Here]
**Federartion** | Permissions | [Add Priority Here]
**Searchsets** | Search Constructor | [Add Priority Here]
**Searchsets** | Search Management | [Add Priority Here]
**Searchsets** | Permissions | [Add Priority Here]
**Searchsets** | Public / Private Search | [Add Priority Here]
**Permissions** | PDM permissions to federated Scene | [Add Priority Here]
**Permissions** | Admin and non Admin permissions | [Add Priority Here]
**Misc** | New Header UI | [Add Priority Here]
**Dependencies** | Save Viewpoint with Search sets | [Add Priority Here]
**Dependencies** | Markups save in a view point | [Add Priority Here]
**Dependencies** | Create viewpoints with searchsets | [Add Priority Here]
**Origin Controller** | Origin Controller UI | [Add Priority Here]
**Appearence Profiler** | Create Appearence Profiles | [Add Priority Here]
**Appearence Profiler** | Save with Views | [Add Priority Here]
**Appearence Profiler** | Save with Search sets | [Add Priority Here]